## Sheet1
Deliverable | Team due date (Expected) | Offical due date (Actual) | TA Comments
Finalize Requirements | 2020-10-21 |  | Be more specific with your requirements. The entire list should be detailed enough to pass it on to a new team to build.
Client Elicitation Meeting |  | 2020-10-23
Q&A Summary from ^ Meeting | 2020-10-24 | 2020-10-25
Prototype V1 | 2020-11-04 | 2020-11-06
SRS Draft v1 | 2020-11-11 | 2020-11-13
Peer Review for SRS & Protype v1
SRS Inspection | 2020-11-14 | 2020-11-16
SRS Draft v2 | 2020-11-23 | 2020-11-25
Prototype V2 | 2020-11-23 | 2020-11-25
Camtasia Video (extra credit) | 2020-11-26 | 2020-11-28
Final Presentation/Demo | 2020-11-29 | 2020-12-02
Final Team Peer Review | 2020-12-03 | 2020-12-04